## ANN-VI SANC WKS
S.No. | Name of work | Location | Client | Zone | Date of sending P.E. | A/A & E/S Amount(in Lakh) | A/A & E/S date | Target date for detail drgs. | Target date for Structural drgs. | Target date for D.E. | Target date for call of tenders | Target date for start of work | Reasons of delay & action proposed
1 | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14
1 | C/o BSF Campus at Lakhnaur SH: Dev. Works. | Lakhnaur | BSF | NZ-I | 514.22 | 514.22 | 2003-06-01
2 | C/o 180 men barrack for BSF at Kharkan. | Kharkan | BSF | NZ-I | 147.39 | 147.39 | 2003-05-01
3 | Pdg. Bulk W/S with 1 No. OHT of 5 lac litre capacity for BSF. | Udhampur | BSF | NZ-I | 138.35 | 138.35 | 2003-08-01
4 | Provision for Bulk services and dev. Works for C/o 2 Nos. 120 men barracks / Administrative block 1 No. Qrtr. Guard-1 No. Hospital 10 bedded and 7 suites with mess for officers 1 No. for Bn Hq. | Bhuj | BSF | WZ-I | 149.77 | 149.77 | 2003-12-01
5 | C/o 30 Nos. T-I qtrs for 137 Bn Hq. | Umpling Shillong | BSF | NEZ | 234.7 | 234.7 | 2003-11-01
6 | C/o Admn. Block for 126 Bn. | Nalkata | BSF | NEZ | 112.12 | 112.12 | 2003-07-01
7 | C/o Admn. Block. | Ambassa | BSF | NEZ | 116.19 | 116.19 | 2003-06-01
8 | C/o 44 Nos. T-II qtrs for Bn HQ at Tura-I. | Tura-I | BSF | NEZ | 263.77 | 263.77 | 2003-06-01
9 | C/o T-II24 qrts for 34 Bn Hq. | Panisagar | BSF | NEZ | 174.41 | 174.41 | 2003-11-01
10 | C/o Functional buildings for NISA. | Hyderabad | CISF | SZ-II | 338.1 | 338.1 | 2003-07-01
11 | C/o mess club. | Barwaha | CISF | CZ | 158.01 | 158.01 | 2003-06-01
12 | C/o Addl. Qrts T-I/52, II/10, III/6, IV/3, V/1 No. | Barwaha | CISF | CZ | 308.89 | 308.89 | 2003-10-01
13 | C/o GO's mess. | Barwaha | CISF | CZ | 165.96 | 165.96 | 2003-04-01
14 | C/o 10 bedded hospital. | Mundali | CISF | EZ-II | 120.35 | 120.35 | 2004-01-01
15 | C/o Trg. Block RTC, Deoli. | Tonk | CISF | NZ-III | 232.94 | 232.94 | 2004-03-01
16 | C/o perimeter wall. | Arrakonam | CISF | SZ-I | 107.93 | 107.93 | 2003-11-01
17 | C/o 32 Nos. T-I, 40 Nos. T-II and 4 Nos. T-III qrs. For GC, CRPF at Kadirpur. SH: C/o 40 Nos. T-II & 4 Nos. T-III qrs at Kadirpur. | Kadirpur | CRPF | ODZ | 191.37 | 191.37 | 2003-07-01 | 2003-07-01
18 | C/o OR's Barrack (60 men) CRPF C/S Head Qr. | Lucknow | CRPF | NZ-II | 121.41 | 121.41 | 2003-06-01 | 2003-06-01
19 | C/o 40 bedded Hospital at GC. | Lucknow | CRPF | NZ-II | 280.74 | 280.74 | 2003-10-01 | 2003-10-01
20 | Admn. Bldg. at Group Centre-I, Ajmer. | Ajmer | CRPF | NZ-III | 162.32 | 162.74 | 2003-09-01 | 2003-09-01
21 | Sewerage Treatment Plant at 1 MLD | Pune | CRPF | WZ-II | 375 | 375 | 2003-09-01 | 2003-09-01
22 | C/o family welfate centre. | Khatkheti | CRPF | NEZ | 121.43 | 121.43 | 2003-09-01 | 2003-09-01
23 | C/o 27 Nos. SO's dormitories. | Imphal | CRPF | NEZ | 239.81 | 239.81 | 2003-08-01 | 2003-08-01
24 | C/o Parade ground, fortwall and spectators gallery at GC, CRPF | Bangalore | CRPF | SZ-III | 110.84 | 110.84 | 2003-08-01 | 2003-08-01
25 | C/o 2 Nos. 405 men barracks for RTC-III. | Paringam | CRPF | SZ-III | 1413.57 | 1413.57 | 2003-03-01 | 2003-03-01
26 | SO's Mess & Dormitory | Paringam | CRPF | SZ-III | 106.9 | 106.9 | 2004-01-01 | 2004-01-01
27 | C/o 93 Qrts (T-I/6, II/40, III/36, IV/9, V/1, VI/1 at Patrika Nagar, Hydrabad. | Hydrabad | SIB | SZ-II | 712.07 | 712.07 | 2003-12-01
28 | C/o Non residential & residential bldg. for SGMI at Sikkim SH: C/o Admn. Building dormitory & DB room, guest house & residential qtr. T-IV/2, II/11 & I/5 Nos. i/c internal W/S, S/I & site development bulk services for civil & electrical and additional wor | Gangtok | SIB | EZ-I | 565.65 | 565.65 | 2003-12-01
29 | C/o Quarter guard. | Shivpuri | ITBP | CZ | 110 | 110 | 2003-04-01
30 | C/o resdidential accommodation. SH T-I/46 Nos. qrs. | Bahlana | ITBP | NZ-I | 130.21 | 130.21 | 2003-07-01
31 | C/o T-I/36, II/24 & III/8 for 17th Bn. | Leh | ITBP | NZ-I | 497.95 | 497.95 | 2004-02-01
33 | C/o Annexe to AG Bldg. Kohima | Kohima | AG | NEZ | 2002-09-01 | 154.97 | 2003-04-01
34 | C/o Resdl. Qtrs. For AG at Kohima (6 Nos. T-I-50 No. T-II 36 Nos. T-III & 12 Nos. T-IV | Kohima | AG | NEZ | 2002-12-01 | 939.95 | 2003-07-01
35 | C/o 152 Nos. AG staff qtrs. At Yousfuda Hyderabad. | Hyderabad | AG | SZ II |  | 852 | 2003-08-01
36 | C/o Admn. & Lab Bldg. for NRCE, Bikaner. | Bikaner | AGR | NZ III | AGR | 111.19 | 2003-11-01
37 | C/O Udya Shanker Academy for Dance & Music at Almorah | Almorah | Culture | NZ.II |  | 475 | 2003-06-01
38 | C/O Parking -cum inter changing shaping & inter portion Centre at Fatehpur Sikheri, Agra. | Fatehpur Sikheri, Agra. | Culture | NZ.II |  | 495.8 | 2003-09-01
39 | C/O Domitory Guest House & parking are at Visharamshati for Durga Sharif, Ajmer. | Ajmer | Culture | NZ.III |  | 187.05 | 2003-11-01
40 | Dev. Of Toursit Circuit, Jaipur, Jodhpur, Jaisalmer, Bikaner and Nagaur. | Jaisalmer | Culture | NZ.III |  | 193.00 644.00
41 | Landscape dev. For Masuria Hills (Veer Durga Smarak) at Jodhpur. | Jodhpur | Culture | NZ.III |  | 152.34 | 2003-11-01
42 | Integrated Dev. Of Tourism Circuit from Adibadri (Haryana) to Dolavira (Gujrat) |  | Culture
43 | C/o Dormitory for visitors, stadium and tent plantform and sulabh souchaly at Mela ground, Pushkar, Ajmer. | Ajmer | Culture | NZ.III |  | 238.57 | 2003-11-01
44 | Area dev. In front of Five Rath at Mohavallipuram | Madhopur | Culture | SZ.I |  | 293.93 | 2003-11-01
45 | Dev. Of Mahabalipuram Shore Temple Madhopur | Madhopur | Culture | SZ.I |  | 277 | 2003-11-01
| a) Sign Ages |  | Culture
| b) Plazas |  | Culture
| c) Lounge & electrical lighting. |  | Culture
46 | Facilities Centre at Fort Cochin. | Cochin | Culture | SZ.III |  | 199.44 | 2003-06-03
47 | Boat Jetty Complext at Ernakulam (a) Pile foundation (b) Superstructure | Ernakulam | Culture | SZ.III |  | 159.92 | 2003-06-03
48 | C/o Bldg. ASI (Epigrapty) at Mysore. | Mysore | Culture | SZ.III |  | 537 | Nov-03
49 | C/O Youth Hostel at Udaipur South Tripura. | Udaipur | Culture | NEZ |  | 144.01 | 2003-08-01
50 | Pdg. Infrastructure locality at Moa Kumakhya Shakti Peeth (PH A) | Guwahati | Culture | NEZ |  | 151.27 | 2003-10-01
51 | Dev. Work in & around Jain Tirthsthan at Pitomia Distt.Bhavnagar,Gujrat. | Bhavnagar | Culture | WZ.I |  | 304.33 | 2003-11-01
52 | Dev. Work in & around Jain Tirthsthan at Gimen Junagarh, Gujrat. | Junagadh | Culture | WZ.I |  | 100.45 | 2003-11-01
53 | Pdg. Laying dia CI pipe from area water line at Timba Cilleso to Tonga Hill | Jhunagadh | Culture | WZ.I |  | 164.00 84.00 | 2003-03-01
54 | C/o Archaeological Museum at Shivpuri. | Shivpuri | Culture | CZ |  | 200 | 2003-06-01
55 | C/o Reception Building at PM House Complex, Race Course Rd., New Delhi. | New Delhi | UD | NDZ I | UD | 212.63 | 2004-01-01
56 | C/o Additional space in existing type 'C' qtrs. at Sector IV DIZ Area New Delhi. | New Delhi | UD | NDZ II | UD | 357.47 | 2003-07-01
57 | C/o Additional space in existing type 'C' qtrs. at Sector IV DIZ Area New Delhi. | New Delhi | UD | NDZ II | UD | 357.47 | 2003-07-01
58 | Development of DDU Park in Pocket 3A | New Delhi | UD | NDZ II |  | 168.75 | 2004-01-01
59 | Redevelopment Scheme of Dev Nagar SH: C/o APTT Hostel G+9 storey ) having dewelling units 196 Nos. | New Delhi | UD | NDZ III | UD | 1035.9 | 2003-04-01
60 | Redevelopment of General Pool housing complex at Aliganj Jor Bagh Road New Delhi SH: T-I-345 Nos. 4 storey i/c development of site) | New Delhi | UD | NDZ III | UD | 1239.17 | 2003-05-01
61 | C/o CBSE bldg. at Mandawali, Fazalpur. | Fazalpur | UD | NDZ-IV | UD | 1616 | 2003-09-01
62 | C/o Office bldg. at Jaipur. | Jaipur | UD | NZ III | UD | 253.59 | 2003-08-01
63 | C/o Addl. Floor over Shastri Bhawan Annexe Bldg. Chennai. | Chennai | UD | SZ-I | UD | - | -
64 | C/o Resdl. Qtrs. For IT Deptt. At Korumondalam SH: C/o 6 Nos. T-I,3 Nos. T-II, 3 Nos. T-III & 6 Nos. T-IV i/c Scooter shed. | Trichy | UD | SZ-I | UD | 309.8 | 2003-12-01
65 | C/o 60 Nos. T-IV qtrs. | Pune | UD | WZ-II | UD | 401 | 2003-06-01
66 | C/o 25 Nos.staff qtrs Central Excies & custome at Alwar (Ty-I-04, Ty-II-05, Ty-III-14, T-IV-2 Nos.) | Alwar | Ex & C | NZ-III | Ex & C | 123.03
67 | C/o CGHS Dispensary building at Sec-19 Kamla Nehru Nagar Ghaziabad (UP). | Ghaziabad | Health | ODZ | Health | 158.77 | 2003-08-01
68 | C/o CGHS Dispensary at Sec-11 Noida. | Noida | Health | ODZ | Health | 100.56 | 2003-09-01
69 | CGHS Dispensary at Shalimar Bagh. | New Delhi | Health | NDZ-III | Health | 108.63 | 2004-02-03
70 | CGHS Dispensary at Shakurbasti. | New Delhi | Health | NDZ-III | Health | 116.81 | 2003-10-01

## ANN-V CMPT WKS
S.NO. | Name of work(i/c Sub Heads) | Location | Client | Zone | A/A & E/S Amount(in Lakh) | A/A & E/S Date | Date of start(as per Agmt) | Stipulated date of completion (as per Agmt) | Head of A/C | Budget Allotment (in Lakh) | Expdr.up to last year (inLakh)=x | Expdr.up to reporting month in current year (in Lakh)=y | Upto date total Expdr. (in Lakh) =x+y | Up to date Physical Progress (%) | Target date of physical completion | Remarks(Present stage of work i/c reason of delay,if any, & action proposed)
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | C/o Admn. Block. | Abohar | BSF | NZ-I | 131.12 | 2001-10-01 | 2002-04-01 | 2003-04-01 | 4055 |  | 61.95 | 14.59 | 76.54 | 100 | 2003-11-01 | Work completed.
2 | C/o 50 Nos. Qtrs SH: T-II/48, IV/2 Nos | Ramtirath | BSF | NZ-I | 155.86 | 2001-05-01 | 2001-12-01 | 2003-01-01 | 4055 |  | - | 7.95 | 115.29 | 99 | 2004-03-01 | Work nearing completion.
3 | C/o 76 Qtrs for Bn SH: T-I/62, II/24 Qtrs. | Humhama | BSF | NZ-I | 221.96 | 2000-05-01 | 2001-02-01 | 2002-06-01 | 4055 |  | 221.59 | 21.84 | 243.43 | 99 | 2004-03-01 | Finishing & defect rectification work in progress.
4 | C/o T-I/48 Nos. (D/S) & II/24 Nos. (D/S) Residential qtrs. | Humhama | BSF | NZ-I | 211.01 | 2000-09-01 | 2001-04-01 | 2002-08-01 | 4055 |  | 176.5 | 15.17 | 191.67 | 99 | 2004-03-01 | Finishing work & rectification work in progress.
5 | C/o Admn. Block for SHQ. | Bikaner | BSF | NZ-III | 111.66 | 2001-10-01 | 2001-11-01 | 2003-02-01 | 4055 (OB) |  | 60.85 | 6.08 | 66.93 | 100 |  | Work completed.
6 | C/o T-II/32 Nos. T-III/2, IV/2 for Bn Hq at Jalipa Distt. | Barmer | BSF | NZ-III | 161.47 | 2001-09-01 | 2001-11-01 | 2003-02-01 | 4055(RB) | 160 | 139.39 | 5.37 | 144.76 | 100 | 2003-12-01 | Work completed and inventories submitted.
7 | C/o 120 men barrack, 4 suites with SO's mess for Bn Hq. Magra Distt. | Barmer | BSF | NZ-III | 217.63 | 2001-06-01 | 2001-11-01 | 2003-02-01 | 4055 |  | 172.7 | 0.57 | 173.27 | 100 | 2003-02-01 | Work completed. Inventory being checked by BSF board.
8 | C/o T-II/12, III/8, IV/4. (b) T-III/4, © T-VI/1 No. | Barmer | BSF | NZ-III | 136.66 | 2001-03-01 | 2001-07-01 | 2002-07-01 | 4055 |  | 96.69 | -1.44 | 95.25 | 100 |  | Work of 28 qtrs completed and handed over except T-V qtrs. Separate tender for T-v qtrs invited.
9 | Admn. Block quarter guard, 10 bedded hospital, 120 men barrack, 4 suites with SO's mess, 7 suites GO's mess at Jalipa Distt. | Barmer | BSF | NZ-III | 375.61 | 2001-07-01 | 2001-11-01 | 2003-05-01 | 4055 |  | 194.3 | 79.08 | 273.38 | 100 | 2003-05-01 | Work completed and inventory submitted to client.
10 | C/o T-II/36, III/04, IV/2 for Bn Hq at Asutar Road. | Ramgarh | BSF | NZ-III | 149.43 | 2001-04-01 | 2001-07-01 | 2002-10-01 | 4055 (RB) | 120 | 125.21 | 8.38 | 133.59 | 99 | 2004-03-01 | The work is almost completed. Final rubbing of floor is in progress.
11 | C/o 120 men barracks, 03 suits for officers (work work) for Bn. Hq at Pokaran-I. | Pokaran | BSF | NZ-III | 116.4 | 2001-12-01 | 2002-03-01 | 2003-09-01 | 4055(OB) | 505 | 48.07 | 45.52 | 93.59 | 100 | 2003-12-01 | Work completed.
12 | C/o 10 bedded hospital 120 men barrack, 07 suites with officers mess for Bn Hq. | Nagaur | BSF | NZ-III | 190.7 | 2001-06-01 | 2001-07-01 | 2002-10-01 | 4055(OB) | 80 | 125.09 |  | 125 | 100 | 2003-11-01 | Work completed and handed over to BSF on 14.11.2003.
13 | Development of campus-II at Tanot Road, Campus-II. | Ramgarh | BSF | NZ-III | 222.42 | 2001-10-01
14 | C/o Admn. Block, quarter guard 120 men barrack, for Tannot Road, Campus-II. | Ramgarh | BSF | NZ-III | 259.12 | 2001-07-01 | 2001-11-01 | 2003-02-01 | 4055(OB) | 505 | 143.74 | 45.96 | 189.7 | 99 | 2004-03-01 | Work almost completed. Finishing work of white washing. Colour washing, distempering and grinding of loors is in progress.
15 | 3 Nos. 120 men barracks with kitchen and dining hall. | Gandhinagar | BSF | WZ-I | 428.31 | 1999-12-01 | 2001-06-01 | 2002-12-01 | 4055 (OB) |  | 207 | 10.44 | 218.24 | 100 | 2003-05-01 | Work completed. BSF has not taken over.
16 | C/o residential qrs 32 Nos. (T-I/12 T-II/12 T-III/ 5 T-IV/4, V/1 No.. | Gandhinagar | BSF | WZ-I | 103.34 | 2002-06-01 | 2001-05-01 | 2002-05-01 | 4055 (RB) |  | 79.55 | 0.04 | 79.59 | 100 | 2003-05-01 | Work completed.
17 | C/o residential qrs 69 Nos. (TII/28 T-III/8, T-IV/4, V/1 No. | Bhuj | BSF | WZ-I | 242.81 | 2000-01-01 | 2001-05-01 | 2002-11-01 | 4055(RB) | 150 | 140.42 | 15.41 | 155.83 | 100 | 2003-05-01 | Work completed.
18 | C/o 1 No. 120 men barracks with kitchen, dining & toilet block for Bn Hq. | Gandhinagar | BSF | WZ-I | 156.76 | 2001-05-01 | 2002-02-01 | 2003-02-01 | 4055 (RB) |  | 59.4 | 3.49 | 62.89 | 100 | 2003-05-01 | Work completed.
19 | C/o 22 Nos. family qrs for Bn HQ (T-II/16, T-I/6 Nos.). | Gandhidham | BSF | WZ-I | 140.81 | 2001-08-01 | 2002-03-01 | 2003-03-01 | 4055(RB) |  | 77.75 | 15.86 | 93.61 | 100 | 2003-10-01 | Work completed.
20 | Dev of site & bulk services SH: C/o storm water drain, sewerage, filtered water supply, OH tank and UGS (W/S). | Kishanganj | BSF | EZ.II | 299.13 | 2000-03-01 | 2002-02-01 | 2002-12-01 |  |  | 467.02 | 767.08 | 544.1 | 99 | 2004-06-01 | Work nearing completion other than storm water drain. Works for storm water drain could be taken up comprehensively only after C/o all the quarters proposed in the campus.
21 | (i) C/o 2 Nos. 168 men barrack with Cook House cum-dining hall (Barrack No.1 (a) Main building (b) Lavatory Block. | Chura Chandpur | BSF | NEZ | 309.05 | 1997-03-01 | 1998-12-01 | 2000-07-01 | 4055 OB(NP) | 30 | 148.55 | 19.85 | 168.4 | 99 | 2004-02-01 | Work in completion stage.
22 | C/o T-I/20 for BSF. | Alamganj-I | BSF | NEZ | 101.54 | 2000-02-01 | 2000-12-01 | 2002-03-01 | 4055 | 120 | 45.16 | 16.43 | 61.59 | 100 | 2003-03-01 | Civil work completed. Elect. Service connection pending.
23 | C/o Boundary wall Security Fencing Gates, Security Post & Guard Room. | Mashimpur | BSF | NEZ | 105.25 | 2000-03-01 | 2001-01-01 | 2002-04-01 | 4055 OB(NP) | 125 | 75.43 | 23.38 | 98.81 | 100 | 2004-01-01 | Work completed.
24 | C/o one No.168 men barracks (excluding cook house and dining hall) at STS II. | Bangalore | BSF | SZ-III | 101.01 | 2002-03-01 | 2002-08-01 | 2003-08-01 | 4055(OB) | 53 | 43.18 | 44.35 | 87.54 | 100 |  | Building portion completed and handed over on 28.10./2003 except septic tank.
25 | C/o 100 Bedded Hospital for BSF at Kadamtala | Kadamtala | BSF | EZ-I | 444.8 | 2000-08-01
26 | C/o CRPF Transit facility cum residential Hostel at Nehru Nagar, New Delhi. | New Delhi | CRPF | NDZ-IV | 276.99 | 26.9.99
27 | C/o 197 Nos. qtrs for GC at Phaphamau. | Allahabad | CRPF | NZ-II | 738 | 2000-09-01
28 | C/o 262 Nos. Residential quarters. | Puna | CRPF | WZ-II | 668.82 (Revised) | 2001-06-01
( c) T-V/3 Nos.
(d) T-III/10 Nos. & IV/3 Nos.
29 | C/o 76 Nos. family qtrs. | Nagpur | CRPF | WZ-II | 330 | NA
30 | C/o 218 Nos. Family qtrs. T-II to T-VI Qtrs. | Pune | CRPF | WZ-II | 1034.02 | 1999-09-01
31 | C/o Men's Club, Canteen, FWC at Primary School. | Pune | CRPF | WZ-II | 215.71 | 2001-08-01
32 | C/o Various Resdl. & Non-Resdl. Qtrs. At GC CRPF Bangarasia. | Bhopal | CRPF | CZ | 1315.19 | 1999-09-01
33 | C/o office cum residential complex (23 Nos. family qtrs) for I.G. B/S DIG and internal audit party at Digha. | Patna | CRPF | EZ-II | 361.36 | 2001-03-01
34 | C/o 4 Nos. 180 men barracks for RAF. | Allahabad | CRPF | NZ-II | 786.63 | 2000-04-01
(a) 3 Nos. 160 men barracks
(b) 1 No. 160 man barracks.
35 | Dev & bulk services. | Allahabad | CRPF | NZ-II | 351.57
(a) C/o Internal W/S, Rods, Sewerline etc.
(b) OHT & UGT/SUMP Wel.
36 | C/o 196 Nos. Residential qtrs for RAF. | Allahabad | CRPF | NZ-II | 681.78
(b) T-II/97 Nos.
(c)T-III/13, IV/8 Nos.
(d) T-V/4, VI/1 No.
37 | C/o 76 Nos. Qtrs for CTC-III. | Mudkhed | CRPF | WZ-I | 309.23
SH: 22 Nos. T-I, 62 Nos. T-II & 2 Nos. T-IV qtrs.
38 | C/o Additional Residential quarters for 7th Reserve Bn for CISF at Amer Jaipur (SH: C/o T-I/48, (F/S) quarters i/c W/S, S/I, drainage, Dev work and internal Elect. Installation. | Jaipur | CISF | NZ-III | 160.96 | 2001-09-01
39 | C/o Non residential bldg for 7th Reserve Bn forCISF at Amer Jasipur (SH:Store Block, Tradesman shop, Training Block and 1 No.180 men barracks i/c W/S, S/I drainage and Elect. Installation. | Jaipur | CISF | NZ-III | 475.19 | 2002-03-01
40 | C/o non residential bldg for 7th Reserve Bn forCISF at Amer Jasipur (SH:GO's mess and SO's mess i/c W/S, S/I, drainage and Elect. Installation. | Jaipur | CISF | NZ-III | 475.19 | 2002-03-01
41 | Bulk services, Miniature Range, UG sump, Roads, Septic Tank, OHT & Elect. Bulk services. | Hyderabad | CISF | SZ-II | 229.05 | 1998-09-01
42 | C/o 2 Nos. 180 men barracks. | Bhilai | CISF | CZ | 488.04 | 2001-07-01
43 | C/o Training Block | Mundali | CISF | EZ-II | 398.91 | 2001-09-01
44 | Administrative cum- communication block. | Mundali | CISF | EZ-II | 366.68 | 2002-05-01
45 | C/o officers mess. | Babeli | ITBP | NZ-I | 382.69 | 2003-04-01
46 | C/o Admn. Block W.T. building. | Pithoragarh | ITBP | NZ-II | 232.96 | 2000-12-01
47 | C/o 10 bedded Mahi-ka-danda. | Mahi-ka-danda | ITBP | NZ-II | 110.54 | 2000-08-01
48 | C/o 10 bedded hospital. | Gaucher | ITBP | NZ-II | 101.76 | 2000-10-01
49 | C/o SO's Dormitory. | Joshimath | ITBP | NZ-II | 102.03 | 2001-12-01
50 | C/o 10 Nos. T-I and 6 Nos. T-II Qtrs for 18 AR's. | Lunglei | AR | NEZ | 140 | 2000-09-01 | 2001-07-01 | 2001-11-01 | 4055 RB(P) | 14 | 116.6 | 28.81 | 145.41 | 100 | 2003-12-01 | Work completed.
8 | Residential & Non residential building for AR's. | Charduar | AR | NEZ | 4066 | 2000-08-01 | 2002-01-01 | 2003-07-01 | 4055 RB(NP) OB(NP) |  | 961.14 | 361.05 | 1322.19 | - | - | Tradesman shop completed & handed over.
51 | C/o 12 Nos. T-I and 6 Nos. T-II Qtrs for 19 AR's. | Serchhip | AR | NEZ | 145.39 | 2000-09-01 | 2001-08-01 | 2002-11-01 | 4055 RB(NP) | 20 | 79.45 | 20.38 | 100.33 | 100 | 2003-12-01 | Work completed.
52 | C/o residential qtrs SMB for 8 NCO & 80 OR's for T-range & 26 AR. | Agartala | AR | NEZ | 365 | 2002-01-01 |  |  | 4055 RB(NP) | 122
| (i) 18 Nos. T-II (T/S). | [5 empty] | 2002-03-01 | 2003-07-01 |  |  | 87.82 | 15.91 | 103.73 | 100 | 2003-11-01 | Work completed.
| (ii) 4 Nos. T-II (D/S). | [5 empty] | 2002-04-01 | 2003-11-01 |  |  | 15.53 | 8.61 | 24.14 | 97 | 2004-02-01 | Brick work in progress.
| (iii) 1 No. T-V (Duplex). | [5 empty] | 2002-05-01 | 2002-09-01 |  |  | 13.89 | 8.69 | 22.58 | 100 | 2003-03-01 | Work completed. Building occupied.
53 | C/o office cum residential completex. | Agartala | SIB | NEZ | 315.62 | 1999-01-01
54 | Essential reapir to HP's Bunglow flats LS/RS Electrical work | New Delhi | UD | NDZ I | 1150
55 | Proposed essential repair in MP flat/bunglow under Divn PWED-11 | New Delhi | UD | NDZ I | 430
(a) | SH Strengthening/augmentation of existing SCC I/c MB/SDB in bunglow |  | UD
(b) | Copper wiring in bunglow |  | UD
© | Copper wiring in Flats. |  | UD
56 | Strengthening/augmentation of SCC to ser qrs I/c improved of internal electrification |  | UD
(a) | Call Bell |  | UD
57 | Modification of gate no 11 at south block new delhi (defence) | New Delhi | UD | NDZ I | 1765.16
c | Providing internal electric installation security lighting |  | UD
d | Water sprinting system |  | UD
e | Pdg. AC system |  | UD
58 | Augmentation of sub station at Nirman Bhawan at New Delhi (GPOA) | New Delhi | UD | NDZ I | 288.58
a | Transformer HT point HT cable IT point and earthing sets etc |  | UD
b | Raising main work |  | UD
59 | Devloping of Bhagwan Mahavir Vanasthali | New Delhi | UD | NDZ I
b | C/o Compound wall with MS Grill. |  | UD
e | Pdg deep tubewell |  | UD
60 | Upgradation of C-2 flats to C2 flats at Bappa Nagar 5 K sub divn GPRA | New Delhi | UD | NDZ II | 107.54
61 | A/A in CSOI KG marg New Delhi 6K Sub Divn(DOPT) | New Delhi | UD | NDZ II | 103.3
b | Service connection, air conditioning and DG set etc |  | UD
62 | C/o 60 Nos. single suit Hostel at Dev Nagar N.D. | New Delhi | UD | NDZ III | 219.44
63 | C/O GPRA for cgesat bemina srinagar (J&K) | Srinagar | UD | NZI | 472.57 / 1528.92
64 | C/O 264 QRTS at simla SH TII/12 No at craighohu longwood GPRA | Srinagar | UD | NZ I | 991.79
65 | C/O general pool type IV - 28 nos (G+7 storeyd) at station road Kolkatta | Kolkatta | UD | EZ I | 356.33
66 | C/o GPRA at lambelin Port Blair TI-36,TII-64,TIII-88 TIV-22 & TVI-10 SH C/O 10 TV qrts | Port Blair | UD | SZ I | 1714
67 | C/O 165 QRTS for GPRA at HSR layout at bangalore PH- B(TIII 60, TIV -90 TV-14, TVI-1) | Bangalore | UD | SZ III | 1585.94
(I) | SH 14 Nos. TV qrts (G+3) |  | UD
(ii) | SH 1 Nos. TVI duplex |  | UD
68 | C/o 1018 qtrs GPRA at CBD belapur Navi Mumbai (TI-50, TII-300, TIII-400, TIV-112 TV-56) SH super structure 92 TII & 28 TV Balance work Electric work | Navi Mumbai | UD | WZ I | 1949
69 | C/o TA &C transit accomodation near G block of NS road Mumbai | Mumbai | UD | WZ I | 491.74 908.75
(a) | SH Pile foundation & super structure |  | UD
(b) | Development work |  | UD
© | Electrification |  | UD
70 | C/o 262 nos GPRA Qtrs C lines at nagpur TI-15, TII 120, TIII 90, TIV 15 TV -12 I/c W/S & S/I & drainage I/c Main work | Nagpur | UD | WZ II | 1285.32
(a) | Prdg IEI & fans in qtrs |  | UD
(b) | Prdg Pump sets |  | UD
© | Prdg street lights |  | UD
71 | C/O B block for GPOA at Nagpur | Nagpur | UD | WZ II | 621.31
72 | Dev. of land approach Rd. drainage C.C. path at Rishab Deo Jain Temple | Udaipur | Culture | NZ-III | 125
73 | Dev. of work at Jain Tirth | Ranakpur | Culture | NZ-III | 130
74 | National Library Bldg. (Bhasha Bhawan) | Calcutta | Culture | EZ-I | 4157
75 | C/o Resdl. Qtrs. Nalanda. SH: C/o T-II 8 Nos. T-III-6, T-IV-12, T-VI-1 No. | Nalanda Bihar | Culture | EZ-II | 185.77
76 | C/o Jai Prakash Narain Memorial Park Bahadur Shah Zafar Marg | New Delhi | Culture | NDZ II | 197
77 | C/o Piligrim amentiy centre at Kullanda Pathonsthti Distt. | Kulanda | Culture | SZ III | 112.74
78 | C/o building for Regional Institute of Unani Medicine at Chennai | Chennai | Health | SZ-I | 299.55
79 | C/o Hosp. And Admn. Block for Indian Institute for Indian Institute of Panchakarma at Cheruthuruthi, Thrissur Dist. | Cheruthuruthi | Health | SZ-III | 100.89
80 | C/o Resd. & Non Resdl. Bldg. For AIIH & PH at Salt Lake (T-I-12, II/4, III/4, IV/12, V/8 & VI/4 (Total 44 Qrs.) | Calcutta | Health | EZ-I | 1982
81 | C/o staff qrs. & international hostel for NIH at JC Block, Salt Lake, Salt Lake, Calcutta. | Calcutta | Health | EZ-I | 337.8
82 | C/o Indian Council Medical Research Lahoal (PH.II) | Lohol | Health | NEZ | 123.08
83 | Installation of DG set voltage regulator capacitor bank at LHMC & SSKH, RML, SJH, ND |  | Health |  | 1034
a) | S/I/T/C of 2x 1700 KVA 11 KV DG set at SJH. | SJH | Health | NDZ-V | 360
b) | S/I/T/C of 2x 1250-0 KVA 11 KV DG set at SJH. |  | Health |  | 260
c) | S/IT/C of 2x 1000 KVA 11 KV DG set at SSKH | SSKH | Health | NDZ-V
e) | S/I/T/C of 2 x2000 KVA 11 KV AVR set at Dr. RMLH | RMLH | Health | NDZ-V | 45
f) | S/I/T/C of 2 x2000 KVA 11 KV AVR set at SSKH | SSKH | Health | NDZ-V | 50
84 | C/o OPD Phase III Right & Left wing of SJH | SJH | Health | NDZ-V | 16440
b) | Lifts | SJH | Health | NDZ-V | 68.64
c) | Fire fighting | SJH | Health | NDZ-V | 6.18
85 | C/o L&R wing of OPD Phill at SJH ND | SJH Complex | Health | NDZ-V | 1644
86 | C/o T-V/8 at Civil Lines.Jaipur | Jaipur | IT | NZ III | 100.22
87 | C/o office cum staff qrs. T-I-8, T-II/77, III/92 Nos.at Sikar. | Sikar | IT | NZ III | 107.1
88 | C/o Internal Partitition, Furniture and AC for IT Deptt. at Vaishali. | Ghaziabad | IT | ODZ | 1045
89 | C/O Income Tax Bldg. at Hissar I/c W/S, S/I, Drinage. | Hissar | IT | NZ-I | 185.25
90 | C/o Office Bldg. and staff qrs. for Income Tax Deptt. at Gulbarga, Karnataka. | Karnataka | IT | SZ-II | 330.3
91 | C/o Office bldg. and staff qrs. for Income Tax Deptt. at Gudiwada. | Gudiwada | IT | SZ-II | 116.96
92 | C/o Office bldg. For I.T. Deptt. at Matigara, | Siliguri | IT | EZ-I | 146.53
93 | C/o Res. & Non Res. Complex at EMBP Cal. For I.Tax Deptt. at Calcutta. | Calcutta | IT | EZ-I | 351.16
94 | Renovation of Scindia House for I.Tax Dept. at Mumbai. | Mumbai | IT | WZ-I | 982.36
95 | C/o Annexe Bldg. for Custom house ,Tuticonn. | Chennai | Ex & C | SZ-I | 267.25
96 | C/O S / Qtrs. for Central Excise Deptt. | Satara | Ex & C | WZ-II | 288.75
97 | C/o Central Excise Office bldg. At EMBP. | Calcutta | Ex & C | EZ-I | 3803
(a) | Foundation work |  | Ex & C
98 | C/o office bldg. And resdl. Qtrs. for Custom and CE at Bethiah. | Betiah | Ex & C | EZ-II | 155.32
(b) | Resdl. |  | Ex & C
99 | C/o Resdl. Qtrs. for Custom Dept. at Nhava Sheva, Navi Mumbai. | Navi Mumbai | Ex & C | WZ-I | 709.5
(a) | Civil work |  | Ex & C
(b) | Elect. Work. |  | Ex & C
100 | C/o Office bldg. For Central Excise Dept. at Panvel, | Navi Mumbai | Ex & C | WZ-I | 339.29
(a) | Civil work |  | Ex & C
(b) | Elect. Work. |  | Ex & C
101 | C/o 20 Nos. (8 Nos.) T.II & 12 Nos. T.III qtrs.) for Central Excise Deptt. at Gorai/Borivali, Mumbai. | Mumbai | Ex & C | WZ-I | 149
102 | C/o Office Bldg. For Central Excise Dept. at Nadiad. | Mumbai | Ex & C | WZ-I | 418.05
103 | C/o 23 Nos. staff qtrs. for RVTI for Women at Salt Lake (PH.I). | Kolkata | Labour | EZ-I | 123.49
104 | C/o Admn. Bldg. & workshop with ancillary work for RVTI for women at salt lake | Kolkata | Labour | EZ-I | 266.24
(a) | Pile foundation work |  | Labour
(b) | Superstructure |  | Labour
105 | C/o Hostel bldg. For RVTI for women at Salt lake | Kolkata | Labour | EZ-I | 222
106 | Resdl. Qrts in 37 Bighas Plot (Ph-I). T-I/48,II/80,III/136, IV/12 Nos. | Agartala | AG | NEZ | 976.33
107 | Residential qtrs for Ph-II. T-I/40, II/96, III/128, IV/8 Nos. | Agartala | AG | NEZ | 963.5
108 | C/o Boundary wall with G.I. Barbed MS gril on top around the land of AG staff qtrs at Lone Hills. | Kohima | AG | NEZ | 104
109 | C/o office building for AGMP I&II. | Gwalior | AG | CZ | 1103.7
110 | C/o 11 Nos. Inland Water Terminals for National Water Way No.3, Kerala at Kottapuram, Thrissur Dist. | Kerala | Shipping | SZ-III | 133.59
(b) | Terminal Bldg. Open storage road & shore protection work. |  | Shipping
111 | C/o 11 Nos. Inland Water Terminals for National Water Way No.3, Kerala at Aluva, Ernakulam Dist. | Aluva | Shipping | SZ-III
(b) | Terminal Bldg. Open storage road & shore protection work. |  | Shipping
112 | C/o 11 Nos. Inland Water Terminals for National Water Way No.3, Kerala at Kayamkulam | Kerala | Shipping | SZ-III | 132.6
(a) | Diaphragm wall |  | Shipping
(b) | Terminal Bldg. Open storage road & shore protection work. |  | Shipping
113 | C/o Locust Office Bldg. in FISL complex | Bikaner, Jaipur | AGR | NZ III | 161.9
114 | C/o V & VI floor over CMFRI cum Lab Bldg. at Cochin. Ernakulam Dist.. | Cochin | AGR | SZ III | 307.2
115 | C/o Facility Research Centre for Fishery Survey of India, Sasoon Dak, Mumbai. Plant Quarantine Lab. Bldg. at Sewri | Mumbai | AGR | WZ-I | 892.85
116 | C/o Plant Quantine Lab Bldg. at Sewri. | Mumbai | AGR | WZ-I | 600.28
117 | C/o Resdl. Qrs.for IMD T.I/4 Nos., II/16, III/16 IV/02, V/2 Nos. | Jaipur | Materology | NZ-III | 183.17
118 | C/o Technical cum office Bldg. for Met Deptt. Hyderabad. | SZ-II | Materology | Hyderabad | 369.5
119 | C/o A-I type school building for KV & 11 Nos. staff qrts at Seoni.. | Malwa | KVS | CZ | 221.2
120 | C/o A-1 type school building for KV at ITBP. | Shivpuri | KVS | CZ | 216
121 | C/o "A" type school building 11 Nos. staff qrts for KV-II. | Indore | KVS | CZ | 222.61
122 | C/o K.V. School at Pragati Vihar, Lodi Road | New Delhi | KVS | NDZ-III | 319.35
123 | C/o A-I single section school bldg. RAU/Pusa. | Bihar | KVS | EZ-II | 130.66
124 | C/o School bldg. Of KV at Angul | Orissa | KVS | EZ-II | 118.61
125 | C/o 'A' Type school Bldg. & staff Qtrs. for KV, CRPF | Gandhinagar | KVS | WZ-I | 223.1
126 | C/O JNV at Chhonkarwara Distt.Bharatpur Ph.B SH:Resdl.Qtrs./ & Hall Dormitory. | Chhonkarwara | NVS | NZ III | 138.38
127 | C/O Bldg. for JNV Khairabad Distt. Kota PH.A | Kota. | NVS | NZ III | 390.07
128 | C/o JNV at Senchua at Golaghat (Ph-B). | Agartala ( Galaghat) | NVS | NEZ | 196.37
129 | C/o building for JNV at Diphu Distt. Karbi Anglong Ph-A. | Assam | NVS | NEZ | 415.29
130 | C/o JNV at Morigaon. | Morigaon | NVS | NEZ | 353.02
131 | C/o JNV at Roing (Ph-A). | Roing | NVS | NEZ | 283.46
132 | C/o school building for JNV at Bishnpur. | Imphal | NVS | NEZ | 180.33
133 | Construction of JNV at Tulnom, C'C'pur. | C'C'pur | NVS | NEZ | 596.81
134 | C/O JNV, Bldg. Hailakandi | Hailakandi | NVS | NEZ | 570.76
135 | C/O JNV, Bldg. | Pallapool Dist, Cachar | NVS | NEZ | 520.76
136 | C/O JNV, Bldg. Ukhrul (Manipur). (b) Balance work. | Manipur | NVS | NEZ | 307.06
137 | C/o JNV Sirmour Phase-B. | Sirmour | NVS | CZ | 177.3
138 | C/O Bldg. for JNV, Sagga Dist., Karnal (HR) | Karnal | NVS | NZ-I | 381.66
139 | C/O JNV at Kunihar Distt. Solan, PH.II C/O 2 Nos. Dormitories (4 blocks) Principal Resdl. 8 Nos. T.II Qtrs. 6 Nos. | Solan | NVS | NZ-I | 163
140 | C/o JNV at Raichur (Ph.A) School bldg. Dormitories kitchen, dining and qtrs. | Raichur | NVS | SZ-II | 462.32
141 | C/o JNV Bldg.Kothidura | Bilaspur | NVS | NZ-I | 149.34
142 | JNV at K'shetra Maholi Distt. Satara (Ph.2) C/O 2 Nos. Dormitories Principal & Warden Resdl. | Satara | NVS | WZ-II | 179.86
143 | JNV at Pimple Jagtap Dist. Pune C/O School Bldg., Boundary wall. | Jagtap, Pune | NVS | WZ-II | 506.46
144 | C/o JNV at Idduki PH'A' Idduki Dist. | Idduki | NVS | SZ-III | 366.08
145 | C/o JNV at Devarahall (PH'A') | Devarahall | NVS | SZ-III | 462.55
146 | C/o JNV at Badami (PH'A') Bagalkot Dist. | Badami | NVS | SZ-III | 443.47
147 | C/o JNV at Nanniyode PH'A'. Trivandrum Dist. | Trivandrum | NVS | SZ-III | 528.3
148 | C/o JNV at Deoti. SH: Dormatories (staff qtrs.and …………. Bldg.) | Bihar | NVS | EZ-II | 493.3
149 | C/o JNV at Araria. | Bihar | NVS | EZ-II | 406.84
150 | C/o JNV Pachari | Darbhanga | NVS | EZ-II | 206
151 | C/o JNV | Champaran | NVS | EZ-II | 538.25
152 | C/o JNV at Kendrapada | Orissa | NVS | EZ-II | 462.1
153 | C/o JNV at Nuapada | Orissa | NVS | EZ-II | 433.94
154 | C/o JNV at Lanwa Distt. Patan (PH.A). | Patan | NVS | WZ-I | 348.95
155 | C/o JNV at Dhansura (PH-B) | Dhansura | NVS | WZ-I | 167.8
156 | C/o JNV at Dahegam (PH-A) Distt. | Gandhinagar | NVS | WZ-I | 442.28
157 | C/o JNV at Trapej, Distt. Bhavnagar | Bhavnagar | NVS | WZ-I | 438
158 | C/o JNV at Mahim, Talpalghar,Distt.Thane. | Thane | NVS | WZ-I | 489.47
Note on F94: cpwd: 1714.00 + 635.02
Note on F109: cpwd: 100 30.00

## ANN-IV MAJOR WRK
S.NO. | Name of work(i/c Sub Heads) | Location | Client | Zone | A/A & E/S Amount(in Lakh) | A/A & E/S Date | Remarks(Present stage of work)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | C/o Storm water drain. | Gidder Galian | BSF | NZ-I | 438.16 | 2000-01-01 | Work in progress.
2 | C/o Admn. Block. | Indreshwar | BSF | NZ-I | 142.74 | 2002-10-01 | Work in progress. Alternative building to be constructed in place of Admn. Block to be intimated by client.
3 | Pdg. Fencing & gate in Trg. Area at STC, Udhampur. | Sunderbani | BSF | NZ-I | 103.6 | 2003-02-01 | Brick work in progress.
4 | C/o Admn. Block 1 No. quarter guard. 1 No. hospital 10 bedded, 7 suits with mess for officers -1 No. for Bn HQ. | Bhuj | BSF | WZ-I | 206.8 | 2000-06-01 | Work in progress.
5 | C/o 38 Nos. T-II qrts for BSF (D/S). | Naranpur Malda | BSF | EZ.I | 143 |  | Work in progress.
6 | C/o 28 Nos. T-II qrts for BSF at Seemanagar. | Seemanagar | BSF | EZ.I | 114.7 |  | Work in progress.
7 | C/o quarters guard for BSF at Bn HQ (192) Bn) | Jalpaiguri | BSF | EZ.I | 104.73 |  | Work in progress.
8 | C/o staff qrs. T-II/56, III/6, IV/2 fir BSF Bn HQ at Sonari, Coochbehar. | CBR | BSF | EZ.I | 150.39 | 2001-11-01 | Work in progress.
9 | C/o staff qrs T-II/58, III/8, IV/2 for BSF Bn HQ at Sonai, Coochbehar. | CBR | BSF | EZ.I | 291.55 | 2001-11-01 | Work in progress.
10 | C/o T-II/20 (D/S) for BSF at SHR Umpling. | Shillong | BSF | NEZ | 131.19 | 2002-07-01 | Felling of trees required to be done. Work in progress.
11 | T-II/16 qtrs. | Bagafa | BSF | NEZ | 132.78 | 2002-11-01 | Work in progress.
12 | C/o residential qrs for Sector HQ. | Teliamura | BSF | NEZ | 209.32 | 2003-01-01 | Work awarded recently.
13 | C/o 48 Nos. T-II residential qrs. | Salbagan | BSF | NEZ | 269.58 | 2003-01-01 | Work in progress.
14 | C/o residential building for new Reserve Bn at Deoli Distt Tonk (SH: T-I/72, (T/s) II/25, (T/s) IV/4 (T/S) V/1 (Duplex) quarters i/c W/S, S/I, drainage and internal Elect. Institute. | Deoli | CISF | NZ-III | 293.98 | 2003-03-01 | Work in progress.
15 | C/o Addl. Qrs for New Reserve Bn (SH: C/o T-I/55 (T/S) II/20, (T/S) III/5 (T/S) i/c W/S, S/I. | Deoli | CISF | NZ-III | 309.01 | 2002-11-01 | Work in progress.
16 | C/o 75 Nos. Addl qrs for New Reserve Bn, Bhilwara (SH: T-I/55(T/S), II/10 (T/S), III/6 Nos (T/S) V/1(Duplex) i/c W/S, S/I. | Tonk | CISF | NZ-III | 266.15 | 2003-03-01 | Work in progress.
17 | C/o Addl qtrs at Amer SH: T-I/56 (F/S) II/10, (F/S) III/6 (T/S) IV/3 (2 Nos. D/S & 1 No.S/S) and V/1 (Duplex) i/c W/S, S/I, drainage, Road work, other dev. Works and internal Elect. Institute. | Jaipur | CISF | NZ-III | 284 | 2003-07-01 | Work awarded recently. Earth work in progress.
18 | C/o SO's Hostel / Mess for 6th RB. | Arakkonam | CISF | SZ-I | 113.7 | 2002-11-01 | In left and right wing brick work reached upto floor 2 level. In rear wing column raised upto lintel level.
19 | C/o 1 No. 180 men barracks for RTC. | Arakkonam | CISF | SZ-I | 172.59 | 2002-12-01 | In left wing roof slab casted. In right wing brick work reached upto floor 3 level. Kitchen & slab roof slab casted. In dining floor 2 slab casted.
20 | C/o SO's Hostel / Mess for 6th RB. | Arakkonam | CISF | SZ-I | 113.7 | 2002-11-01 | Floor-II slabs casted. Brick work reached up to lintel/floor level.
21 | C/o 180 men barracks for RTC. | Arakkonam | CISF | SZ-I | 172.59 | 2002-12-01 | Work in progress.
22 | C/o Group Head quarters for NISA. | Hyderabad | CISF | SZ-II | 343.43 | 1998-09-01 | Work just started.
23 | C/o GO's mess for RTC, CISF. | Bhilai | CISF | CZ | 111.44 | 2002-05-01 | Work awarded recently.
24 | C/o Admn. Block & Communication Centre. | Bhilai | CISF | CZ | 117.02 | 2003-10-01 | Work awarded recently.
25 | C/o 2 Nos. 180 men barracks for RB. | Bhilai | CISF | CZ | 440.63 | 2002-08-01 | Work awarded recently.
26 | 3 Nos. 180 Men's Barracks (Now 4 1/2 No. 120 men barracks are being constructed). | Mundali | CISF | EZ-II | 881.09 | 2002-03-01 | Block 1 RCC in foundation 60% Block II Yet to start Block III G.F. columns 50% casted, Block IV RCC in foundation 80%, Block V RCC in foundation 20%.
27 | CISF complex Indirapuram PH-II Additional 69 Nos. family qtrs (T-I/49, II/15, III/5) | Indirapuram | CISF | ODZ | 213.11 | 2003-03-01 | (i) Slab of one block of T-I is at roof level and 4 block at lintel level done. (ii) T-II brick work in progress in superstructure (iii) T-III work in progress under plinth.
28 | C/o CISF campus at Indirapuram, Ghaziabad Ph-II Additional 75 Nos. Family qrs (T-I/55, II/10, III/6 & V/1 ) i/c I/W/S , S/I and Elect. Etc. | Indirapuram | CISF | ODZ | 247.51 | 2003-04-01 | Work in progress, roof casting level-I.
29 | C/o 2 Nos. 180 Men barracks for GC, CRPF, at kadirpur, Gurgaon (Now 3 Nos. 120 Men barracks) | Kadirpur | CRPF | ODZ | 559.99 | 2001-10-01 | Footing completed in one barrack column reached upto floor two level and in other two barracks castings of columns and plinth beams is in progress.
30 | C/o 62 Nos. Family quarters at Kadirpur, Gurgaon SH: 45 Nos. T-II & 14 Nos. T-III Qrs.i/c internal W/S & S/I and electrification etc. | Kadirpur | CRPF | ODZ | 261.98 | 2002-09-01 | 3 Type II qrs. At plinth level. Foundation of T-III qtrs. Completed and casting of plinth beam in progress.
31 | C/o 1 No. 180 man barrack for CRPF Phaphamau. | Allahabad | CRPF | NZ-II | 260.46 | - | Superstructure in progress.
32 | C/o Store Block for GC. | Allahabad | CRPF | NZ-II | 186.61 | 2002-11-01 | Foundation in progress.
33 | C/o Officer's Mess & suits Central Sector, Gomti Nagar. | Lucknow | CRPF | NZ-II | 110.46 | - | Work in progress.
34 | Pdg. Bulk services & development work at CS(HQ) at Gomti Nagar. | Lucknow | CRPF | NZ-II | 100.71 | - | Work in progress
35 | C/o 1 No. 180 men barrack at GC. | Lucknow | CRPF | NZ-II | 272.17 | - | Earth work in progress.
36 | C/o SO's mess & Dormitory for 108 Bn RAF. | Aligarh | CRPF | NZ-II | 171.22 | 2002-12-01 | Work in progress
37 | C/o 79 Nos. Family qtrs T-I/75 (F/S) & III/4 Nos. (D/S) at GC. | Rampur | CRPF | NZ-II | 233 | - | Site for T-I qtrs not available for construction due to standing trees.
38 | C/o 310 Nos. qtrs. For (i) CRPF at GC-II, Ajmer (SH: T-I/8, II/123, i/e W/S, W/I, drainage Road other development works & internal electrical installation. | Ajmer | CRPF | NZ-III | 1375.58 | 2002-12-01 | Work is in progress.
39 | C/o 325 Nos. qtrs. for CRPF. | Ajmer | CRPF | NZ-III | 1270.1 | 2003-01-01 | Work is in progress.
40 | C/o Boundary wall around CRPF at GC-I, Ajmer. (i) SH: T-III/30 Nos. (F/S) T-V/2 Nos. (Duplex). | Ajmer | CRPF | NZ-III | 105.89 | 2003-05-01 | Work in progress.
41 | C/o 325 Nos. Qrs at GC-I (SH: T-I/50, i/c W/S, S/I, Drainage, Road other dev. Works and internal elect. Installation). | Ajmer | CRPF | NZ-III | 1270.1 | 2003-01-01 | Work is in progress.
42 | C/o 1 No. 180 men barrack for GC. | Gandhi Nagar | CRPF | WZ-I | 206.16 | 2001-11-01 | Work is in progress.
43 | C/o Addl. W/S line CRPF. | Telegaon | CRPF | WZ-II | 126.63 | 2003-05-01 | Work in progress.
44 | C/o 262 Nos. Residential quarters. | Puna | CRPF | WZ-II | 668.82 (Revised) | 2001-06-01 | Work completed and handed over.
45 | C/o 186 Nos. residential qrs | Neemuch | CRPF | CZ | 685.63 | 2001-08-01 | Work just awarded
46 | C/o SO's Dormitory for 54 personal & Ktichen block at GC, CRPF, Bangarasia, Bhopal. | Bhopal | CRPF | CZ | 124.8 | 2001-12-01 | Work in progress.
47 | C/o CRPF complex at Salt Lake, Pile Foundation. | Kolkata | CRPF | EZ-I | 353.77 | - | Work in progress.
48 | C/o 73 Nos. addl. Family qtrs. For CRPF Avadi,Chennai | Avadi Chennai | CRPF | SZ-I | 388.59 | 2002-07-01 | Structural work in progress.
49 | C/o Admn. Bldg. for 105 Bn. RAF at Coimbatore. | Coimbatore | CRPF | SZ-I | 105.34 | 2002-08-01 | Flooring & finishing in progress.
50 | C/o 1 No. 180 Men barrack at CTC II, CRPF, | Coimbatore | CRPF | SZ-I | 222.11 | 2002-11-01 | Structural work completed. Finishing works in progress.
51 | C/o 1 No. 180 Men Barracks for CRPF GC, Jawahar nagar, RR Distt. | Hyderabad | CRPF | SZ-II | 226.97 | 2003-02-01 | Finishing work in progress.
52 | C/o Admn. Block for 99 Bn RAF at J/Nagar. | Hyderabad | CRPF | SZ-II | 102.2 | 2002-08-01 | Work in progress.
53 | 180 Men Barrack GC, CRPF, Bangalore (4th) | Bangalore | CRPF | SZ-III | 296 | 2003-02-01 | Work in progress.
54 | C/o office cum residential qrs for SIB. | Kottayam | SIB | SZ-III | 136.76 | 2002-08-01 | Work in progress.
55 | C/o residential quarters T-II/24 No 1st Bn. | Sarhan | ITBP | NZ-I | 110.34 | 2002-09-01 | Earth /rock cutting for levelling work is in progress.
56 | C/o administrative block. | Reckong Reo | ITBP | NZ-I | 159.883 | 2001-02-01 | Work awarded. Earth work in progress.
57 | C/o covered foot path front B/wall, storm water drains & other dev works near officer's mess. | Babeli | ITBP | NZ-I | 414.52 | 2005-09-01 | Fixing grills in progress.
58 | C/o residential qtrs T-II/24 No. 1st Bn. | Sarhan | ITBP | NZ-I | 478.18 | 2004-04-01 | Earth /rock cutting for levelling work is in progress.
59 | C/o additional 120 men barrack with kitchen & dining hall for ITBP campus. | Sarhan | ITBP | NZ-I | 510.01 | 2006-09-01 | Cutting of trees removal / shed S&LT line. RCC work in progress.
60 | C/o 24 Nos. T-I qtrs (T/S). | Pithoragarh | ITBP | NZ-II | 121.91 | 2002-08-01 | Work just started.
61 | C/o MT garrage for 13th Bn at Gaucher. | Gaucher | ITBP | NZ-II | 123.13 | 2000-11-01 | Work in progress.
62 | C/o 32 No.1 Qtrs. | Matli | ITBP | NZ-II | 131.94 | 2002-09-01 | Work started.
63 | C/o 24 Nos. T-III Qrs at Seemadwar. | Dehradun | ITBP | NZ-II | 115.99 | 2003-07-01 | Work recently awarded.
64 | C/o Recreation Centre & JCO's accommodation at ARTC & S. | Diphu | AR | NEZ | 317 | 2002-02-01 | Work in progress.
65 | C/o Residential qrs at Khatla, Mizoram (i) 24/II, 8/III, 1/IV. (ii) 4 Single JCO accommodation. | Mizoram | AR | NEZ | 279 | 2002-02-01 | Work in progress.
66 | Modification of gate no 11 at south block New Delhi GPOA | New Delhi | UD | NDZ I | 211.5 | 2002-05-01 | Work in progress.
67 | C/o Guest House for Central Govt. Employees at Kidwai Nagar | New Delhi | UD | NDZ-III | 213.83 | 1996-05-01 | Structure work started.
68 | C/o Samaj Sadan Bldg. at Sector-IV, R.K.Puram, New Delhi. | R.K.Puram | UD | NDZ-III | 200.17 | 2001-02-01 | Structure work in progress.
69 | C/o Samaj Sadan at Sector -I, MB Road, New Delhi. | New Delhi | UD | NDZ-IV | 214.23 | 2001-11-01 | Foundation work upto plinth level progress.
70 | C/O 264 QRTS at simla SH TII/12 No at craighohu longwood GPRA | srinagar | UD | NZ I | 991.79 | 1995-02-01 | Work delayed due to non approval of plan from simlaTI-12 .
71 | C/o Kendriya Bhawan for Central Govt. Office in Bareilly. (SH: Purchase of land & C/o Boundary wall | Bareilly | UD | NZ II | 125.2 | - | Land purchased in 11/02. Work of Boundary wall is in progress.
72 | C/O 220 no staffQrts for GPRA at flat No 6 Sec 3 Vidyadhar nagar Jaipur(T1-64 ,T11 - 88,T111 64) 216 nos component | Jaipur | UD | NZ III | 986 | 2002-08-01 | Work recently started.
73 | Restoration & upkeeping of two government place (west) Kolkatta | Kolkatta | UD | EZ I | 143.16 | - | Work in progress
74 | C/O GPRA at gandhigram (T-II 32, TIII 48 TIV 12, TV-4) Agartala | Agartala | UD | NEZ | 690.29 | 2002-11-01 | Work in progress.
75 | C/O transit hostel for CPWD at cochin | Cochin | UD | SZ III | 325.3 | 2002-03-01 | Work in progress
76 | C/o TA &C transit accomodation near G block of NS road Mumbai | Mumbai | UD | WZ I | 491.74 908.75 | Jan- 95 August 2003 | Work in progress.
77 | SH Pile foundation & super structure
78 | C/o GPRA 33 nos Qrts C/o 6 nos TII, 17 no TIII, 8nos TIV & TV at bomblin prdg S1 E1 and fans | Bambolin | UD | WZ II | 239.49 | 2002-08-01 | Work in progress. Out of 33 no qtrs slab costed for 25 nos.
79 | C/o National Gallery of Modern Art at Jaipur House, New Delhi. | New Delhi | Culture | NDZ-IV | 4945 | 2002-06-01 | Work in progress.
80 | Area Dev. In front of Five Rathas at Mahabalipuram | Coimbatore | Culture | SZ-I | 299.83 (300.00 ) | 2002-12-01 | Site not handed over by client. Balance work hold up.
81 | Compound wall & door & 101 shops. |  |  |  | - | - | Work in progress.
82 | C/o Cultural Complex at Chowkaghat Varanasi. SH: Multipurpose Hall. | Varanasi | Culture | NZ-II | 206.70 (334.08) | 2002-07-01 | Work in progress.Casting of double height slab completed. Stone clading in progress. Internal finishing & flooring in progress.
83 | C/o Great Vista at Haridwar | Haridwar | Culture | NZ-II | 394 | 2002-12-01 | Work in progress.
84 | C/o Youth Hostel at Badrinath Dham, Badrinath. | Badrinath | Culture | NZ-II | 165.91 | 2002-03-01 | Work just started.
85 | C/o History Museum at Shaheed Smark | Ballia | Culture | NZ-II | 276.99 | 2002-12-01 | Foundation 80%. Bldg. lintel level.
86 | Renovation of Manickyavelu Mansion for NGMA at Palace Road, Bangalore. (a) Civil. (b) Internal EI. | Bangalore | Culture | SZ-III | 777.71 | 2001-12-01 | Work in progress. PQ under process for fire & UPS PQ called for A/C . PQ approved for Lift.
87 | Dev. Work in and around Kshatriya Kund at Lachhaur, Jamui (Bihar). | Jamui (Bihar) | Culture | EZ-II | 125 | 2002-05-01 | Work in progress
88 | C/o Tourist Complex at Thanmukkam Alpppazha Dist. PH I, II, III. | Thanner mukkam | Culture | SZ III | 149.15 | 2001-11-01 | Work in progress.
89 | C/o Cottage for Punmudi Civil works | Punmudi | Culture | SZ III | 116.63 | 2000-10-01 | Work in progress.
90 | C/o Interpotation cum shoping complex NODS(a) Civil works.(b) Development work. |  | Culture | SZ III | 495 | 2003-01-01 | Excavation in progress.
91 | Development work Bhavanagar | Bhavnagar | Culture | WZ-I | 303.33 | 2002-11-01 | Work in progress.
92 | Development work in Anand Jain Tirthsthan at Junagarh Gujrat | Junagadh | Culture | WZ-I | 186.45 | 2002-11-01 | Work in progress.
93 | Development place for Sant Tukaram Temple at Dohi Civil amneities | Pune | Culture | WZ-II | 100 | 2003-08-03 | Work in progress.
94 | Development work at Alandi. | Pune | Culture | WZ-II | 100 | 2003-08-03 | Work recently awarded.
95 | Refurnishing of Agakhan Palace. | Pune | Culture | WZ-II | 250 | 2003-10-01 | Work in progress.
96 | C/o Extension of Lecture Block of NIA at Jaipur I/c W/S, S/I drainage and Elect. Insttallation. | Jaipur | Health | NZ III | 482.32 | 2001-10-01 | Delay due to non-allotment of budget.
97 | C/o Laboratory building for HPL and PLIM. Elect. | Ghaziabad | Health | ODZ | 1317 | 2000-12-01 | Work in progress.
98 | C/o National Institute of Sidda at Tambaram.Hostel Nurses & staff qrs. Of Admn. Block. | Chennai | Health | SZ-I | 2000 | 2002-03-01 | Work in progress.
99 | C/o 20 Nos. qtrs. For MT Bangalore. | Bangalore | Health | SZ-III | 137.22 | 2002-08-01 | Work in progress.
100 | C/o Building for Child Development Centre at Thirumathi Buerau | Trivandrum | Health | SZ-III | 545.62 | 2002-08-01 | Work in progress. Report awaited.
101 | Expansion and upgradation of the existing casuality and emergency services for DR RMLH | SJH | Health | NDZ-V | 2813 | 2002-07-01 | Work in progress.
102 | Trauma Centre Bldg. at Dr. RMLH ND | RMLH | Health | NDZ-V | 1000 | 2002-07-01 | Work started.
103 | C/o 206 Nos. Residential qrs at Malviya Nagar. | Jaipur | IT | NZ III | 877.67 | - | Work in progress.
104 | C/o Internal Partitition, Furniture and AC for IT Deptt. at Vaishali. | Ghaziabad | IT | ODZ | 1045 | 1999-01-01 | Work nearing completion.
105 | C/o Income Tax Towers at AC Guards, Hyderabad | Hyderabad | IT | SZ-II | 2605.55 | 2002-07-01 | Foundation in progress. Civil work under progress. Tender awarded from IEI. Lowest tender accepted by CE (E).
106 | C/O 111 S/Qrs. for I.T Deptt. at Rd.No.10, Banjara Hills, Hyd. | Hyderabad | IT | SZ-II | 1254.06 | 2002-03-01 | Work in progress.
107 | C/o Main Admn. Cum-lab Bldg. I/c External Development W/S & S/I at IIPR, Kanpur | Kanpur | IT | NZ-II | 315.5 | 2000-03-01 | Finishing work in progress.
108 | C/o 220 Nos. staff qrs. For IT Deptt. at IIMT layout | Bangalore | IT | SZ-III | 1293.11 | 2002-07-01 | Work in progress.
109 | C/o Office bldg. For I.T. Deptt. at Quilon Kolam Distt. | Kollam | IT | SZ-III | 188.24 | 2002-09-01 | Test pile report submitted.
110 | C/o 22 Nos. staff qtrs. For Deptt. At Mangalore | Mangalore | IT | SZ-III | 129.44 | 2003-02-01 | Work in progress.
111 | C/o Res. & Non Res. Complex at EMBP Cal. For I.Tax Deptt. at Calcutta. | Calcutta | IT | EZ-I | 351.16 | 2002-06-01 | Work in progress.
112 | C/o Office Bldg. & Resdl. Qtrs. for I.Tax Dept. at Nadiad. | Mumbai | IT | WZ-I | 214.65 | 1999-02-01 | Tender accepted. T-III & T-V. Balance work in progress.
113 | C/o Divisional office and Range office for Central Excise & Custom Deptt at Surya Nagar. | Alwar | Ex & C | NZ-III | 179.82 |  | Work in progress.
114 | C/o Office Bldg. For the staff of Custom and Central Excise Division and range offices at Bharuch. | Bharuch Bhuj | Ex & C | WZ-I | 177.5 |  | Work in progress.
115 | Extension of Hostel at Sector-24, Noida. | Noida | Labour | ODZ | 127 | 2002-12-01 | Excavation started.
116 | C/o RLC office building at Kanpur. | Kanpur | Labour | NZ-II | 133.64 | 2003-02-01 | Work in progress
117 | C/o 2 Nos. T-VI qrts & 6 Nos. T-V qtrs for Group officers at Jatia. | Guwahati | AG | NEZ | 179 | 2000-05-01
118 | Development of bulk services. | [5 empty] | Work in progress.
119 | C/O Office Bldg. for AG(Pb) PH.II Sec.17, CHD. | Chandigarh | AG | NZ-I | 1318.49 | 2000-10-01 | Work in progress.
120 | C/O 4 Nos. T.VI Qrs. for AG, AP | Hyderabad | AG | SZ-II | 134.4 | 2000-12-01 | Development work in progress.
121 | C/o Office bldg. For AG at Gangtok | Sikkim | AG | EZ-I | 497 | 22/8/00 | Work in progress.
122 | Annexe to AG Bldg. | Kohima | AG | NEZ | 154.87 | 2003-04-01 | Work recently awarded.
123 | C/o Shore Based Marine Academy at Karave, Navi Mumbai. | Navi Mumbai | Shipping | WZ-I
124 | Swimming Pool- Ph.II |  | Shipping |  | 322.53 | 2000-12-01 | Work in progress.
125 | C/o Inland water transport terminal bldg. at Gaighat Patna. | Patna | Shipping | EZ-II | 1435 | 1998-02-01 | Work in progress. Casting & sinking of all the walls are in progress. Work was hampered due to flooding in garrage.
126 | C/o 11 Nos. IWTs for National Water Way No.3 Kerala at Vaikom. | Kerala | Shipping | SZ-III | 119.32 |  | Work in progress.
127 | Terminal Bldg. Open storage road & shore protection work. |  | Shipping |  |  |  | Work in progress.
128 | C/o 11 Nos. IWTs for National Water Way No.3 Kerala at Thrikkunnappuzha | Kerala | Shipping | SZ-III | 132.16
129 | Diaphragm wall and Terminal Bldg. |  | Shipping |  |  |  | Tender recalled for under scrutiny.
130 | C/o 11 Nos. Inland Water Terminals for National Water Way No.3, Kerala at Cherthala. | Kerala | Shipping | SZ-III | 123.84
131 | Diaphragm wall |  | Shipping |  |  |  | Tenders recalled.
132 | Terminal Bldg. Open storage road & shore protection work. |  | Shipping |  |  |  | Completed upto pile cap.
133 | C/O Lab cum Admn. Block for CITH | Srinagar | AGR | NZ-I | 200 | 2000-03-01 | Addl. Room for Elect. S/System & for Centrally heating required supplement any agreement to be drawn.
134 | C/o New Laboratory building for NPPTI at R' Nagar, Hyd. | Hyderaabd | AGR | SZ-II | 166.41 | 2001-02-02 | Finishing work in progress.
135 | Conference Hall & Director's office at NAARM | Hyderaabd | AGR | SZ-II | 142.69 | 2004-03-01 | RCC column in GF in progress.
136 | Regional Drug Testing Lab. | Hyderabad | AGR | SZ-II | 441.16 | 2001-04-01 | RCC column in GF in progress.
137 | C/o Facility Research Centre for Fishery Survey of India, Sasoon Dak, Mumbai. Plant Quarantine Lab. Bldg. at Sewri | Mumbai | AGR | WZ-I | 892.85 | 2000-02-01 | Work held up due to stay order of Mumbai High Court.
138 | C/o 30 Nos. Resdl. Qtrs.for Survey of India at Sector-13, Gandhi Nagar. | Gandhi Nagar | SOI | WZ-I | 147.04 | 2002-03-01 | Work awarded. Local body approval awaited because of dispute of renewal of ownership and lease.
139 | C/o Office Bldg. for SOI at Plot No.20 Sector-10 Vidyadhar Nagar, Jaipur. | Jaipur | SOI | NZ-III | 145.05 | 2002-02-01 | Work in progress & is below lintel.
140 | C/o Office & Museum Bldg. for Anthropological Survey of India at Udaipur. | Udaipur | SOI | NZ-III | 352.55 | 2003-12-01 | Work in progress.
141 | C/o Dopplor Roder Stn. At Kailashgiri Vizag. | Vizag | Materology | SZ-II | 164 | 2001-10-01 | Work just awarded.
142 | C/O JNV at Leh. | Leh | NVS | NZ-I | 758.73 | 2000-03-01
143 | C/o School Bldg. for KV at Bhilwara | Jaipur | KVS | NZ-III | 136.8 | 2002-08-01 | Work in progress.
144 | C/o School Bldg. for KV SH: Canteen , Scooter Shed | Bhilwara Jaipur | KVS | NZ-III | 136.8 | 2002-02-01 | Work in progress.
145 | C/o KV at Dabla Distt Jaisalmer. | Jaisalmer Rajasthan | KVS | NZ-III | 144.22 | 2003-03-01 | Work in progress.
146 | C/o A-I Type School bldg. for KV CRPF | Khatkhati | KVS | NEZ | 282.51 | 2003-11-01 | Work for qrs. In progress. Tender for school bldg. in progress.

## ANN- III GPOA
Zone | Brief Name of work & Location | In progress during the year (Sqm.) | Target during the year (sqm.) | Completed upto 12/03
1 | 2 | 3 | 4 | 5
NZ II | GPOA at Vidyadhar, Jaipur | 608.24 | 608.24 | 608.24
SZ III | GPOA at Thrikkara, Cochin | 16288 | 2000 | -
WZ-I | GPOA at Navi Mumbai | 15452 | 15452 | -
| Total: |  | 18060.24

## ANN- II GPRA
S.No. | Zone | City | Type of Quarters (Nos.) | [5 empty] | Hostel |  |  | Achievement upto Ist Qtr. Ending June'2002
|  |  | T-I | T-II | T-III | T-IV | T-V | T-VI | SS | DS | Total
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 10
1 | NDZ-IV | New Delhi/R.K.Puram | - | - | - | 24 | 94 | - | - | - | 118 | 118
2 | NDZ-IV | New Delhi/Andrews Ganj | - | - | - | 314 | 200 | - | - | - | 514
3 | NDZ-IV | Dev Nagar | - | - | - | - | - | - | 60 | - | 60
4 | NZ-I | Srinagar | - | - | - | 18 |  |  |  |  | 18 | 65%
5 | NZ-I | Simla | - | 10 | - | - | - | - | - | - | 10
6 | NZ-II | Agra | 15 | 30 | 60 | 8 | - | - | - | - | 113 | 86%
7 | NZ-III | Bikaner | 6 | 6 | 8 | 1 | - | - | - |  | 21 | 99%
8 | WZ-I | Mumbai/New Mumbai | - | - | 92 | - | 28 | - | T-C-13 T-A-57 | - | 190
9 | EZ-I | Calcutta | - | - | - | 28 | 36 | - | - | - | 64
10 | SZ-I | Chennai | - | - | - | - | 5 | - | - | - | 5
11 | SZ-I | Port Blair | 36 | 63 | 88 | 22 | 10 | - | - | - | 219
12 | SZ-III | Bangalore | - | - | - | - | 1 | - | - | - | 1
13 | SZ-III | Trivandrum | - | - | 54 | 30 | - | - | - | - | 84
14 | NEZ | Agartala, Gandhidham | - | - | - | 48 | 12 | 4 | - | - | 64
|  | Total: | 57 | 109 | 350 | 457 | 378 | 0 | 130 | 0 | 1481

## ANN-I WL
Period | Construction i/c Deposit works | Maintenance i/c Deposit work | Total in Fiancial terms | Total workload 2+3x2.25
1 | 2 | 3 | 4 | 5
Total workload for the year 2003-2004 | 1843.74 | 753.16 | 2596.9 | 3538.35