## Central Design Organisation

For The Year2003-2004

| S. No. | ITEM/JOB Identified for this year | Target for the year 2003-04 | Achievement upto March 2004 | Remarks |
| --- | --- | --- | --- | --- |
| 1. | Central Excise Office Building at Kolkata. | Issue of all drawings for super-structure | Structural Drawings of six blocks issued and remaining two blocks drg. upto 2nd floor issued. | - |
| 2. | C/o Income Tax Office Building at Kolkata. | Issue of drawings for super-structure upto 4th floor | Structural Drawings upto roof level of side blocks and eighth floor drgs of central block issued. |  |
| 3. | C/o NABARD Bldg. at Lucknow | Issue of all drawings for super-structure. | Structural Drawings upto roof level and all drawings of service block issued. |  |
| 4. | C/o GPO Bldg. Pushpa Bhavan, New Delhi. | Finalisation of structural system. | Structural sizes intimated to the architect in June 03.. | Arch. drgs. incorporating structural sizes awaited. |
| 5. | Vardhman Medical College New Delhi | Finalisation of structural system | Structural sizes intimated to the architect in Sept. 03. | Arch. drgs. incorporating structural sizes awaited |
| 6. | C/o General Pool Office Complex,CBD,Shahdara. | Finalisation of structural system | Structural sizes intimated to the architect in Aug.03. | Arch. drgs. incorporating structural sizes awaited |
| 7. | C/o Extension of Parliament Annexe Bldg. | Finalisation of structural system | Structural sizes intimated to the architect in Sept. 03. | Arch. drgs. incorporating structural sizes awaited. |
| 8. | C/o Director General of Commercial Intelligence & Statistics, Kolkata (DGCI&S) | Issue of all drawings for super structure | Preliminary str. Analysis completed. Structural system finalised and intimated to Architect in Oct. 03. | - |
| 9 | C/o All India Institute of Hygiene & Public Health, Salt Lake, Kolkata (Institutional Block) | Finalisation of structural system | Structural sizes intimated to the architect in Oct. 03. | - |
| 10. | C/o Office Building for UPSC at Shahjahan Road, New Delhi. | Any further reference | 100% |  |
| 11 | C/o National Museum, Ph. III, New Delhi | Issue of drawing for foundation | Structural sizes intimated to the architect in May 2002 | Detailed Architectural drawing awaited |
| 12. | C/o General Pool Office Building, INA Colony, New Delhi. | Issue of structural drawing for foundation | Strc. Sizes intimated to Architect in Dec. 03. |  |
| 13. | C/o of office building for CBSE FAZALPUR | Issue of structural drawings for foundation |  |  |
| 14. | Printing and distribution of Manual on Repair and Rehabilitation of Reinforced concrete structure. | Printing to be completed | Handbook released on 5.8.03 and distribution on progress Approx.600 books distributed |  |
| 15. | National Gallery of Modern Art, New Delhi. | Issue of structural drawings for all three blocks upto level two | Structural drawings issued for two blocks. | Revision in Architectural drawings. |
| 16. | Preliminary sizes of Administrative block, Hostel and Auditorium, CRPF Campus, Kadirpur. | Finalisation of structural system and structural sizes. | Structural sizes sent to architect in August 2003. |  |
| 17. | Training Institute for Cabinet Secretariat R&D Block, Gurgaon | Issue of structural drawings upto plinth level | Structural drawings for foundation and columns issued. |  |
| 18. | Repair & Rehabilitation report. | 7 reports | 5 reports |  |
| 19. | Developing program for Graphical Interface of full Raft and support selected columns and thereafter integrating it seamlessly with IADB | 100% | 100% |  |
| 20 | Updating Integrated Planning Application for changes and additions issued by S&S and additional feature | 100% | 100% |  |
| 21. | Implementation of computerized Divisional Accounting System | 100% | Training completed in Delhi and other regions except part ER and Border region. Implemented in more than 180 divisions.(50%) |  |
| 22. | Up-dation of Employees Information System and uploading it on CPWD Website | 100% | Development of Web-based Application in progress through NIC. |  |
| 23. 24. 25. 26. | Design work of C/o Handicraft Bhawan for NIDC at New Delhi. C/o Special type 26 nos. MP`s flats for Rajya Sabha at New Delhi. C/o RTI & Computer Centre for IT Deptt. at Kolkata C/o Four Storeyed Car Parking Building for IT Deptt. at Kolkata | Issue of structural design 100% Issue of structural design. 100% Issue of Load Moment Chart Issue of Load Moment Chart | 100% 100% 100% 100% |  |
| 27. | Environment Friendly Materials Technology : Wood Substitute. |  |  |  |
|  | (i) FRP Shutters (ii) Secondary wood shutters like Rubber wood Eucalyptus Wood (iii) PVC shutter | Performance to be reviewed & approval of renewal of manufacturers to be considered 100% | 100% | (i)Renewal of FRP shutters issued (ii)Renewal of “Drosam” door shutters under process (iii)One firm for PVC Door shutters approved. |
| 28. | Energy efficient technology | At least one such technology to be studied and developed for use 50% | 25% | - Use of bamboo in building being identified - Fly ash concrete inter-locking block for masonry work under process for approval |
| 29. | Approval of New materials | Available material will be - considered for approval for use on trial basis. 10 Nos. - Review of performance and renewal of approval of old materials already approved for test use. 10 Nos. | 18 no. Products 10 no. Products. | CPEC meeting held on 23.12.03 |
| 30. | (i)Testing of Material l (ii) Soil Investigation | - Testing of building material of CPWD field unit and other department. - Solid investigation for building foundation - To earn revenue of 30 lacs | Rs..61.78 lakh | - |