Annnexure - 7

Annual Report of

Central Designs Organisation, CPWD

2004-2005

| S. No. | Item/Job Identified for this year | #### Target for the current year 2004-05 | Achievement upto 31st Dec.04 | Remarks |
| --- | --- | --- | --- | --- |
| 1. | Central Excise Office Building at Kolkata. | Issue of all drawings for super-structure | Completed |  |
| 2. | C/o Income Tax Office Building at Kolkata. | Issue of all drawings for super-structure | Completed |  |
| 3. | C/o NABARD Bldg. at Lucknow | Issue of all drawings for super-structure. | Completed |  |
| 4. | C/o GPO Bldg. Pushpa Bhavan, New Delhi. | Finalisation of structural analysis. | Arch. drgs. awaited |  |
| 5. | Vardhman Medical College Safdarjung, New Delhi | Finalisation of structural analysis. | Approved Arch. drgs. awaited |  |
| 6. | C/o General Pool Office Building, INA Colony, New Delhi. | Issue of structural drawings for foundation. | Approved Arch. drgs. awaited |  |
| 7. | C/o Extension of Parliament Annexe Bldg. | Finalisation of structural analysis. | Arch. drg. awaited. |  |
| 8. | C/o Director General of Commercial Intelligence & Statistics, Kolkata (DGCI&S) | Issue of all drawings for super-structure | Load Movement Chart revised for foundation design. |  |
| 9 | C/o All India Institute of Hygiene & Public Health, Salt Lake, Kolkata (Institutional Block) | Finalisation of structural system | Structural system finalised |  |
| 10. | C/o National Museum, Ph. III, New Delhi. | Issue of drawings for foundation | Arch. Drgs. awaited. |  |
| 11 | Structural design of National Gallery of Modern Art, Jaipur House | All the structural drawings to be completed by Aug. 2004. | Completed. |  |
| 12. | C/0 26 Nos. special type MP Flats at BD Marg, New Delhi | All structural drawings to be issued. | Completed. |  |
| 13. | C/o RTI, Comp. Centre, Hostel for IT Deptt. at EM Bye Pass, Kolkata, CE,EZ-1 | All structural drawings to be issued. | Completed upto 9th floor. | Terrace floor drg. is to be issued. |
| 14. | C/o 4 Storeyed Car Parking for IT Deptt. at EM Bye-Pass, Kolkata, CE,EZ- | All structural drawings to be issued. | Completed. |  |
| 15. | CBSE, Mandawali, Fazalpur. | Foundation drg. | Analysis completed. | Details of electric room loading received late. |
| 16. | Arranging Technical Presentations ( in nos.) | 25 Nos. | 8 Nos. | Response from field unit is very slow. |
| 17 | Establishment of LAN in 4 Buildings in New Delhi | 100% | Completed in East Block | Response of NIC is very poor. |
| 18. | Development of Personal Information Management System | 100% | Under implementation |  |
|  | Implementation of Divisional Accounting System | 100% | Completed. |  |
|  | Approval of new building materials | 10 Products to be approved | One products approved (FRP shutters) | Meeting of Central Product Evaluation Committee conducted for 12 products upto 31.12.2004. |
|  | Testing Materials by CPWD and other deptts. | Rs. 40 lacs | Rs. 46 lacs. |  |
| 23. | Preparation of Analysis of rate of special R&R items given in R&R Manual | A/R of all the items in all the sub head shall be ready for approval | Sub-head-I and II partly completed. | Shall be completed by 31.3.2005. |
| 24. | Investigation Reports suggesting remedial measures | 8 cases | 6 cases. |  |