## CSQ report Annexure-10
Sr. No. | NAME OF WORK IDENTIFIED FOR THE YEAR | CLIENT | COST (Rs. IN LAKHS) | Target for the year | ACHIEVEMENTS DURING THE QUARTER In % | CUMULATIVE ACHIEVEMENT DURING THE YEAR in % | REMARKS
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | GTB Hospital Project at Shahdara, Delhi | CE PWD (Zone III) (NCTD) |  |  |  |  | All Structural Design of Library issued. Structural sizes of Auditorium sent to SA (DGHS) Final architectural drawings awaited.
| a) Library block |  | 190 | -- | - | -
| b) Auditorium EE-I |  | - | 90 | - | -
2 | Office Bldg for National Centre for Agricultural Economic & Policy Research (NCAP) at Pusa, New Delhi – Structural Design EE-II | CE(NDZ) III | 337 | 50 | 50 | 100 | Architectural drawings issued by SA-XII. All the structural drawings including water tank issued.
3 | Nuclear Science Centre, New Delhi(Ph. II) Arch Planning & Design and Structural Design EE-II,/ Arch | CE(NDZ) III | 800 | 10 | 100 | 100 | Architectural, Structural drawings for all buildings issued.
4 | SFS Flats for DDA at Motiakhan, Delhi (12storeyed) Str Design EE-II | DDA | 400 | 25 | 5 | 95 | Structural Drawings for columns, Stair case, slabs issued & beam drawings upto level 11 issued
5 | Pucca School Bldg at Vasundra Enclave, Delhi EE-I | CE Zone II (NCTD) | 263 | 15 |  | 15 | DE issued. Part foundation design issued. Other Structural design work is also in hand. Consultancy charges not yet received.
6 | Pucca School Building at J & K block, Dilshad Garden, Delhi. EE-I | -do- | 480 | 55 | - | 10 | Detailed Estimate already sent.
7 | JNV at Madhapura, Bihar (Ph. B) EE-II, Arch | NVS | 285 | - | - | - | Work completed Revised LOP & Str drgs issued. Fee awaited
8 | Samaj Sadan at Lodi Road, New Delhi EE-I | CE (NDZ)III | 190 | 100 | 50 | 80 | Structural drawings upto Roof level issued.
9 | MEA works at Kabul, Afghanistan. | MEA
| i) New Chancery Building |  | - | 100 | 100 | 100 | PE amounting Rs.38.32 Crore sent on 05.10.2004
| ii) Repair & Rehabilitation of Habibia school at Kabul , Afghanistan E E-II, Arch |  | - | 100 | 90 | 90 | -----
10 | Renovation/rehabilitation of IGICH at Kabul | MEA |  | 70 | 10 | 50 | PE cum DE submitted on 02.5.03 E/S received , D.E. prepared, draft Tender document issued. Work is in progress
11 | Road work ;for MOST Phase I EE(Geo) | MOST | 3484 |  | - | - | PE & DE sanctioned. Fee awaited
12 | MEA Quarters at Chanakyapuri, New Delhi Structural Design EE | CE (NDZ)III | 1652 |  | - | - | Str sizes sent to SA IVA/A & E/S awaited. Further work not taken up.
13 | 2 Nos 180 Men Barracks for CRPF at Kadirpur, Gurgaon Str. Design EE - III | CE(ODZ) | 559 |  | - | - | Scope of PE & DE of work changed
14 | Bldg for Homeopathy Pharmacy Lab at Ghaziabad (UP) Str. Design EE-III | CE(ODZ) | 1317 | 1 | 4 | 100 | All the drawings issued.
15 | Institute of Social Defence at Pappankala, Delhi Str. Design EE(Geo) | CE(ODZ) | 464 |  | - | - | To keep in abeyance as informed by SE(P&A)
16 | Police Station Bldg. at Mansrovar Park, Delhi | CE(NCTD) Zone II | 327 |  | - |  | DE submitted, Project withdrawn
Str. Design & detailed estimate EE-III
17 | Police Station Bldg. at Jaffarabad , Delhi Str. Design & detailed estimate EE-III | CE(NCTD) Zone II | 514 |  | - | - | DE submitted, Project withdrawn
18 | C/o Jetty at Pandu, Guwahati EE-II/ Arch | CE(NEZ ) Shillong | 3000 | 50 | 10 | 50 | DE , Draft NIT, drawings of well foundation, layout issued. The concept of super structure is to be changed as per direction of ADG(TD)
19 | C/o RCC Jetty at Patna | IWAI | 2500 | 100 | - | 99 | Architectural and structural drawings issued.
20 | C/o High Level RCC Jetty at Pandu, Guwahati | IWAI | - | - | - | - | Work is being transferred to CDO, CPWD., New Delhi.
21 | Foreign Service Institute at New Delhi | CE (NDZ)III |  |  |  |  | All Structural design for Inst. Block and Hostel block issued
| Str Design a) Office block |  | 1200 | _ | _ | _
| b) Hostel block |  |  |  | - | -
| c) Residential Block EE-III |  |  | 45 | 15 | 95
22 | Tripura State Guest House at New Delhi. Str Design EE- | -do- | 300 | _ | - | - | All Drawings issued.
23 | UT Guest House at Chanakyapuri, New Delhi Str Design I EE -III | -do- | 700 |  | - | - | All Drawings issued.
24 | Afro Asian Legal Consultative Committee Bldg. at Chanakyapuri, New Delhi. Str Design EE (Geot) | -do- |  |  | - | 5 | Drawings issued.
25 | Earthquake risk evaluation centre at Aya Nagar, Delhi. EE(Geo) | Metrological Department | 2500 |  | - | - | Fee awaited.
26 | Handicraft Bhawan at Baba Kharak Singh Marg, New Delhi. Arch | Textile Ministry | 1100 | 5 | - | 5 | DE +Arch. Drawings issued .
27 | Constn. of Type V qurts for Delhi Jal Board at Lajpat Nagar New Delhi.-1100024 | Delhi Jal Board | 135 | -- | 70 | 100 | Detailed estimate & Arch. Drawings issued. Structural design also issued.
28 | C/O ITI for Women at Vivek Vihar N.Delhi. EE-III | CE, PWD Zone-II | 212 | 70 | 20 | 50 | DE has been finalized & sent structural analysis completed drawing under preparation.
29 | C/O Fire Station & Staff Qrts. At Dallupura N.D. EE-III | CE, PWD Zone-II | 234 | 75 | 15 | 40 | DE sent. Structural analysis completed Design & Detail under progress.
30 | C/O additional block in between Admn. & ExitBlock | - | - |  | - | - | P/E amounting to Rs. 276.00 lakh in Feb.03
31 | Undertaking the complete technical checkup of the work executed for NIAW Ballabhgarh, Faridabad | M/O Statistics & Programme Impt | - |  | - | - | Consultancy Fee Rs. 2,02,500/- received on 26.12.02
32 | Redevelopment of Devnager Delhi | NDZ-III | 1829 | 100 | 0.5 | 0.5 | A/A & E/S received for 1829 lakh on 26.11.2002 Structural sizes are being worked outPreliminary sizes for hostel block issued Planning work is to be done by CE (NDZ) III, CPWD, New Delhi.
C/O Type-I/ 90 Nos., T-II/ 360 Nos.(4 storeyed)
| C/O APT Hostel (G+9)/196 units |  | 1036 |  | - | -
C/O T-III(G+10) 640 Nos. with basement
| C/O T-III(G+10) 400 Nos. with basement, |  | 852 |  | - | -
| T-IV(G+10)/18 Nos. with basement |  | 10941 |  | - | -
33 | Master plan of ICAR campus Pusa New Delhi. | CE, NDZ-III |  |  |  |  | Requirement from client are still awaited
34 | C/o 64/80 Bedded Maternity and care Hospital at Nasir Pur , Dwarka New Delhi. | EE,PWD-27 New Delhi. | - |  | - | - | Terms & Condition for proof Consultancy sent vide No. CS/P-31/602 dated 19/9/03 required consent is awaited.
35 | i ) C/o Indira Gandhi Instt of Physical Education & Support Science at Sector 3 ,Rohini New Delhi | CE, PWD Zone III Delhi | - |  | - | - | Terms & Conditions for comprehensive Consultancy sent to client vide NoCSO/P-31/603 dt 19.9.03. Required consent is awaited.
| ii) C/o Jail Building at Narela Delhi |  | _ | _ | _ | _ | -do-
36 | C/o CWC Library and Information Bureau at RK Puram, New Delhi. | SE DCC-XII CPWD, New Delhi. | 576 | 93 | 5 | 100 | All structural drawings issued
37 | C/o Cardio Neuro Tower in AIIMS New Delhi. | SE AIIMS Ansari Nagar N.Delhi |  | 98 | 15 | 45 | Change of structural sub consultant. Design philosophy and structural analysis submitted by the sub consultant is under scrutiny.
38 | C/o Central school at Various locations (16 Nos.) | KVS Delhi | - | 85 | 5 | 30 | Preliminary architectural drawing & Estimates for 10 stations sent (as per requisition of KVS). A/A & E/S awaited. 2 nos. DE sent. Two DE & structural analysis is in progress.
39 | C/o 500 bedded Hospital at Dwarka, New Delhi | EE,PWD-27 | - | - | - | - | Terms & Condition for proof Consultancy sent vide No. CS/P31/178 dated 12/03/2004 required consent is awaited.
40 | Vetting of Projects for North Eastern States and Sikkim | MOUD & MOUEPA | __ | __ | __ | __ | Total 8 Nos. Project reports amounting Rs. 80 crore were scrutinized during quarter ending Sept.04.
41 | Repairs & Rehabilitation of Habibia School at Kabul. | MEA |  |  | 10 | 90 | Work at site is in progress NIT’s for all the works, structural drawings, for roof slab and Cycle shed already issued.
42 | C/O Afghan Parliament house at Kabul (Afghanistan) | MEA |  |  | - | - | Input from Govt. of Afghanistan to Committee in India awaited.
43 | The work Pradhan Mantri Gram Sadak Yojana “PMGSY” | Min. of Rural Development | - | - | - | - | For Development of rural roads in Bihar
44 | The work of Rashtriya Sam Vikas Yojana “RSVY” | MOSRTH | - | - | -- | - | For Development of roads in Bihar
45 | C/o Resident doctors hostel at RML Hospital | SE, DCCX, CPWD | 13 | - | 5 | 95 | Total fee received all the structural drawings except stair case issued and will be issued shortly.
46 | C/o Vertical extension of laundry block at RML | SE, DCC-X, CPWD | - | - | 100 | 100 | Non feasible report sent.
47 | C/o HPL & PLIM at Kamla Nehru Nagar, Ghaziabad | CE(ODZ), CPWD | 1317 | - | 2 | 100 | All structural drawings issued.
48 | Estimate for completion of Auditorium & Gymnasium in Sanskriti School, Chanakyapuri, N Delhi | DoPT | 300 | 100 | 100 | 100 | Estimate vetted